## QE Responsibilities
Action | Completed? | Timing | Hazard Category | Risk
Host a Food Safety and Sanitary Design kick off meeting |  | 1 Design Planning | General | Project Execution Excellence
Develop/update water control program to address moisture sources in the new system (water use by QRO exception only) - GUIDANCE DOCUMENT IS BEING DEVELOPED |  | 1 Design Planning | Biological | Microorganisms - All
Deliver GMP, food safety, and Sanitary Design Principles training for contractors |  | 1 Design Planning | General | Project Execution Excellence
All GMI QRO, Engineering and Sanitation leads complete Sanitary Design Principles course |  | 1 Design Planning | General | Project Execution Excellence
Include key food safety events to project timeline (e.g. validation, passivation, regulatory inspection) |  | 1 Design Planning | General | Project Execution Excellence
Food safety is included in project budgeting (e.g. increased swabbing, increased cleaning, increased supplies) |  | 1 Design Planning | General | Project Execution Excellence
Temporary update of EMP (environmental monitoring program) to an elevated state before/during/after project work |  | 1 Design Planning | Biological | Microorganisms - Pathogens
Identify and approve all Critical Control Points (CCPs) and Control Points (CPs) |  | 1 Design Planning | Chem, Phy, Bio | All
Complete a food safety risk assessment (biological, phyical, chemical, regulatory) |  | 1 Design Planning | Chem, Phy, Bio | All
Temporarily update water control program to address water/moisture during project (condensation, leaks, cleaning) |  | 2 Active Construction | Biological | Microorganisms - All
Develop a cleaning, housekeeping, and auditing schedule for construction areas |  | 2 Active Construction | Physical | Metal, Wood, Plastics, Glass
Agree on time and resource (including inspectors, maintenance, etc.) needs for changeovers to meet Food Safety success criteria |  | 2 Active Construction | General | Project Execution Excellence
Update plant approved chemical list based on input from vendors/suppliers/contractors |  | 3 - CQV Execution | Chemical | Equipment chemicals
Update Allergen Control Program to address any changes (cleaning, color coding, storage) |  | 3 - CQV Execution | Chemical | Allergens
Update glass, brittle plastic, and ceramic program to address any new hazards to the system |  | 3 - CQV Execution | Physical | Metal, Wood, Plastics, Glass
transition plan from construction zone to a GMP zone |  | 3 - CQV Execution | Chem, Phy, Bio | All
update Sanitation and inspection training |  | 3 - CQV Execution | General | Project Execution Excellence
Debrief and communicate learnings to broader QE and Sanitation communities |  | 4 Debrief | General | Project Execution Excellence

## Sanitation Responsibilities
Action | Completed? | Timing | Hazard Category | Risk | Resources | s | Completion Date | Action Taken
Determine the appropriate cleaning method (dry, wet, controlled wet) for all equipment |  | 1 Design Planning | Biological | Microorganisms | Sanitation Lead
Complete the Chemical Recommendation Process document for all wet cleaning methods with Ecolab rep |  | 1 Design Planning |  |  | Chemical Supplier
Include project food safety Success Criteria Form items in pest control providers annual objectives |  | 1 Design Planning | Biological | Pests | Sanitation Lead
create/update sanitation work instructions (i.e. SSOPs, OPLs, CILs, etc.) w/chemicals and parameters |  | 1 Design Planning | Chemical | Sanitation chemicals: alkaline, acid, sanitizer | Chemical Supplier
include food safety Success Criteria Form items in Ecolab (or other chemical supplier) annual objectives |  | 1 Design Planning | General | Project Execution Excellence | Chemical Supplier
Develop a Changeover Matrix to address all changeover types (including, but not limited to allergens) |  | 1 Design Planning | General | Project Execution Excellence | Sanitation Lead
Complete a QCO (quick change over) assessment to ensure sanitation is as efficient as possible (wash bay capacity, minimized need for tools, cleaning/storage racks) |  | 1 Design Planning | General | Project Execution Excellence
Will the construction zone be designed to accommodate the needs for food safety and sanitation utilities (hot water, steam, high pressure water, vacuum system, etc.)? |  | 1 Design Planning | General | Project Execution Excellence
update maps, order new equipment (traps, fogging systems, etc) |  | 2 Active Construction | Biological | Pests | Pest Control Provider
Temporarily update MSS (master sanitation schedule) and PMs (preventative maintenance) to address environmental changes (e.g. increased frequency of inspection/cleaning, filter changes) |  | 2 Active Construction | Biological | Microorganisms - All | Sanitation Lead
Update sanitation programs to include new areas/equipment (MSS, Validation report, Verication and Monintoring program, and SSOPs) |  | 2 Active Construction | Chem, Phy, Bio | All | Sanitation Lead
complete an initial clean of incoming equipment (see CQV tab on Success Criteria Form) |  | 2 Active Construction | Physical | Metal, Wood, Plastics, Glass | Sanitation Lead
plan for passivation of new stainless steel equipment |  | 3 - CQV Execution | Chemical | Sanitation chemicals: alkaline, acid, sanitizer | Chemical Supplier
Note on G1: Karl Thorson: Accountable (approver, 1)
Note on H1: Karl Thorson: Responsible (do-er, 1)

## Eng Responsibilities
Action | Timing | Hazard Category | Risk | Resources | Responsible | Completion Date | Action Taken
Design review for the elimination/mediation of condensation risk in the process and during cleaning | 1 Design Planning | Biological | Microorganisms - All | Engineering | CSA Engineer
Design for water removal (drains, slopped floors, drip pans, etc) | 1 Design Planning | Biological | Microorganisms - Pathogens | Engineering | CSA Engineer
highlight RTE (ready to eat) vs non-RTE zones and inputs on project engineering drawings | 1 Design Planning | Biological | Microorganisms - Pathogens | Engineering | CSA Engineer
Design for food safety and sanitation utilities needs (hot water, steam, high pressure water, vacuum system, etc.) | 1 Design Planning | General | Project Execution Excellence | Engineering | CSA Engineer
controlled entry and exit planning during construction activities | 1 Design Planning | Chem, Phy, Bio | All | SCOE | Project Engineer
Identify construction vs processing areas on the facility map and address with proper containment | 1 Design Planning | Chem, Phy, Bio | All | Engineering | Project Engineer
highlight equipment key access points for routine sanitation and maintenance on project engineering installation drawings | 1 Design Planning | Chem, Phy, Bio | All | Engineering | Project Engineer
highlight zones and inputs for uncommon allergens on project engineering drawings (equipment and receiving) | 1 Design Planning | Chemical | Allergens | Engineering | Project Engineer
request and budget for sanitation related equipment: new foamers, hoses, air drops, COP tank, hand sinks | 1 Design Planning | General | Project Execution Excellence | SCOE | Project Engineer
Sanitary Design and Tranfered Equipment checklist is completed for used equipment that will be relocated | 1 Design Planning | General | Project Execution Excellence | SCOE | Project Engineer
Sanitary Design checklist is used during key VAT/FATs (vendor/factory acceptance test) | 1 Design Planning | General | Project Execution Excellence | SCOE | Project Engineer
Sanitary Design checklist is completed by the equipment vendor prior to the VATs | 1 Design Planning | General | Project Execution Excellence | Equipment Manufacturers | Project Engineer
Determine open product zone protection plan (e.g. cleanable overheads or sheilding) | 1 Design Planning | Physical | Metal, Wood, Plastics, Glass | Engineering | Project Engineer
Identify and approve all control points (CCPs & CPs) on the engineering drawings | 1 Design Planning | Physical | Metal, Wood, Plastics, Glass | Engineering | Project Engineer
Create PMs for all Sanitation and Food Safety related equipment (e.g. metal detectors, foamers, CIP systems) | 2 Active Construction | General | Project Execution Excellence | Reliability Lead | Maintenance TL
request manuals for all new equipment to include cleaning procedures | 2 Active Construction | Chem, Phy, Bio | all | Equipment Manufacturers | Project Engineer
Develop a plan to control hot work and demolition activities | 2 Active Construction | Physical | Metal, Wood, Plastics, Glass | SCOE | Project Engineer
Determine any existing equipment removal/demolition plans (if needed) | 2 Design Planning | Chem, Phy, Bio | All |  | Project Engineer
Work with SCOE to ensure complaince with specific CIP validation criteria | 2 Design Planning | Biological | Microorganisms | SCOE | Project Engineer
HVAC and room air flow planning complete pre and post project work | 1 Design Planning | Biological | Microorganisms |  | Project Engineer
Plan for passivation of new stainless steel equipment | 2 Design Planning | Chem, Phy, Bio |  |  | Project Engineer
Has a plan for passivation of new stainless steel equipment been established?
Note on F1: Karl Thorson: Responsible (do-er, 1)