## ORA
Third Party/Contractor/Supplier/Resource (equipment or chemical supplier)
Project Overall Risk Assessment - Review
Name of Project Owner: __________________________________________
|  | Project Name/Number | Yes | No | N/A | Is Follow-up Required? | Comments Attached? | Person Responsible | Maintenance | Quality | Sanitation | Engineering | Manufacturing/Operations | Safety/Environmental | Food Safety/Regulatory
1 | Risk Management - General
| 1.01 | Has the appropriate Corporate and Plant Site Risk Managers been assigned?
| 1.02 | Have the appropriate Corporate and Plant Site Risk Managers review this document and reviewed all follow up activities with the Project Manager?
| 1.03 | If a review has been done, have any changes been made to the project since that review and has the Project Manager incorporated these recommendations into the scope of the project?
| 1.04 | Are Material Safety Data Sheets (MSDS) available for all new materials?
| 1.05 | Has the QA Manager and Sanitation Supervisor been briefed on the project?
2 | Environmental - General
| 2.01 | Is there a formula or standards change?
| 2.02 | Will new chemicals and / or raw materials be brought into the plant?
| 2.03 | Will there be any changes to air, sewer, other waste water, or solid and hazardous waste emissions?
| 2.04 | If any changes, have they been quantified and reviewed with the Site Environmental Leader for concurrence?
| 2.05 | Will there be any changes to equipment or process speed?
| 2.06 | Will any new pollution control equipment be installed?
| 2.07 | Will any changes be made to pollution controlling equipment, like hoods, baghouses, waste treatment facilities, etc.?
| 2.08 | Will any wetlands be affected?
| 2.09 | Will the project be doing any yard and underground trenching?
| 2.1 | Will any new tanks, above or below ground be constructed?
| 2.11 | Will any new permits, permit changes, or agency notifications be needed?
| 2.12 | Could this project create an odor issue?
| 2.13 | Have all necessary clearances been obtained?
2 | Fire Protection
| 3.01 | Are there any changes in the Fire Protection System such as: fire walls, fire doors, sprinkler systems, smoke vents, or heating, ventilating, and air conditioning (HVAC) ducts through fire walls?
| 3.02 | Is there a change in the business interruption potential due to the project?
| 3.03 | Will there be any changes as a result of the project that will impact on current materials stored or storage conditions, new materials being introduced, and change to an existing process or a new process that will have an impact on sprinkler systems?
| 3.04 | Will there be any changes to material storage density or types of material stored or processed impacting sprinkler density?
4 | Industrial Hygiene and Safety - General
| 4.01 | Will existing equipment be modified? | [6 empty] | x | x | x | x |  | x | x | x
| 4.02 | Is any equipment new to the manufacturing facility or Company? | [6 empty] | x | x |  | x | x
| 4.03 | Are Guarding or Energy Lockouts required? | [11 empty] | x |  | x
| 4.04 | Will pedestrian and / or vehicle traffic patterns be altered or created? | [11 empty] | x
| 4.05 | What equipment will required operator interaction such as feeding, supplying, jam clearing, cleaning, etc.? | [10 empty] | x
| 4.06 | If equipment is being installed in existing facilities, will any points of restricted access likely result? i.e. confined space | [9 empty] | x |  | x |  | x | *
| 4.07 | Will hardware or facilities require people to go to different working surface levels to operate or maintain the system? Will platforms or ladders be required? | [6 empty] | x |  |  |  | x | x | x
| 4.08 | Will lifting tasks be required? Will people be required to lift more than 20 pounds? | [11 empty] | x |  | x
| 4.09 | Will "confined spaces" be created? | [11 empty] | x |  | x
| 4.1 | Will any chemicals be used or created in the process which have a health hazard, a reactivity rating , be flammable, or have a pH not between 3 and 11? | [6 empty] | x |  | x |  |  | x |  | x
| 4.11 | Will any gas be used in the process which could be an asphyxiate (inert gas blanketing, etc.)? | [11 empty] | x |  | x
| 4.12 | Will any equipment have surface temperatures greater than 130° F? | [11 empty] | x
| 4.13 | Will new battery charging areas be created? | [11 empty] | x
| 4.14 | Is any "noisy" equipment being installed? (> 80 dbA at 3 feet) | [11 empty] | x
| 4.15 | Will any new equipment cause work areas to be above 85 dbA? | [11 empty] | x
| 4.16 | Will the project introduce any ergonomic risk factors, such as repetitive motion, awkward postures, motions involving high forces., etc.? | [11 empty] | x
| 4.17 | Are any new chemicals being brought in that could have a toxic or sensitizing effect on people? | [6 empty] | x |  | x |  |  | x |  | x
| 4.18 | Will an radiation or laser sources be installed or relocated? | [11 empty] | x
| 4.19 | Will safety showers / eyewash stations be added? | [11 empty] | x
| 4.2 | Is there any reason to believe that there will be increased dust or other particulate levels as a result of the changes? | [11 empty] | x | x
| 4.21 | Is there a need for a Hazardous Systems Analysis? Is so is funding provided? | [11 empty] | x | x
| 4.22 | Will air sampling be required? | [11 empty] | x | x
| 4.23 | Will there be a need for respiratory protective equipment? If yes, what type? | [11 empty] | x
| 4.24 | Will there be a need for other personal protective equipment? If so, what type(s)? | [11 empty] | x
5 | Industrial Hygiene and Safety - Key Ingredients
| 5.01 | Does a formula change involve a change in the amount or type of enzyme?
| 5.02 | Is current raw enzyme, enzyme dust handling equipment affected?
| 5.03 | Will medical monitoring (such as skin prick testing) be required prior to start-up?
6 | Technical Safety - Combustion and Thermal Safety
| 6.01 | Will there be any new combustors, e.g. boilers, direct fired heaters, furnaces, etc.?
| 6.02 | Will there be any changes to steam, fuel, or other systems and utilities, etc.?
| 6.03 | Have funds been included to complete the necessary combustion safety studies?
| 6.04 | Are energy source flows being moved, added, deleted or changed?
| 6.05 | Does the equipment contain an open flame for a combustion engine?
7 | Technical Safety - Process & Pressure Vessel Safety
| 7.01 | Will you be installing or modifying process piping and / or equipment? Examples : piping, valves, tanks, pumps, instruments, logic, safety devices, etc.?
| 7.02 | Does this project involve any flammable, combustible, or hazardous materials? Does the process involve OSHA 1910.119 chemical or process?
| 7.03 | Are you adding or deleting any pressure vessel, or modifying any existing pressure vessels?
| 7.04 | Are you including funds to update P&IDs and Electrical Plans?
| 7.05 | Are you including funds to complete a Process Safety Study or PHA?
| 7.06 | Are you adding or modifying heat exchangers, or any Above or Underground Storage Tanks?
8 | Technical Safety - Electrical Power Systems Safety
| 8.01 | Is additional horsepower being added that will affect substation capacity? Will the affect the short circuit and coordination study?
| 8.02 | Are feeders and Power Distribution Panels (PDPs) adequate?
| 8.03 | Will you be installing underground circuit?
| 8.04 | Is grounding required?
| 8.05 | Do you have funds to update electrical drawings or PHA? Will this be including the single line?
| 8.06 | Are there any changes to instrument systems?
| 8.07 | Are Robotics being installed?
9 | Technical Safety - Welding Safety
| 9.01 | Will there be welding, cutting, grinding, or open flames?
| 9.02 | Will you be fabricating / purchasing and tanks or pressure vessels?
| 9.03 | Will there be any equipment fabricated by outside vendors? Are the welders qualified and does the project require certified welders?
| 9.04 | Will the plant or contractor do the on-site welding?
| 9.05 | Do you need a welding inspector?
10 | Technical Safety - Fire
| 10.01 | What fire equipment changes are being made? Where?
| 10.02 | Are any fire walls or load bearing walls affected?
| 10.03 | Are any walls being moved / removed?
| 10.04 | Are any entrances or exits being moved, blocked, added?
11 | Americans with Disabilities Act - US Only
| 11.01 | Will new building facilities be erected (such as offices, conference rooms, stairs, elevators, walkways, doors, lockers rooms, etc.)?
| 11.02 | Are new rest rooms being installed?
| 11.03 | Will new parking lots be installed?
| 11.04 | Will new drinking fountains or telephone be installed?
12 | Hazardous Material Transportation - DOT - US Only
| 12.01 | Are hazardous materials going to be received at the plant in bulk and / or semi-bulk (drums, totes, etc.)?
| 12.02 | Will existing incoming or outgoing traffic be affected?
| 12.03 | Will there be any outbound shipments of hazardous material, either bulk or non-bulk?
13 | Security - Project
| 13.01 | Will you be bringing in contractors, construction workers, or operational personnel? Are they Union / Non-Union?
| 13.02 | Are the necessary confidential Disclosure Agreement (CDAs) in place?
| 13.03 | Have you addressed parking, key cards, safety inspections, safe practices, etc. with contractors?
| 13.04 | Will you be creating confidential drawings?
| 13.05 | Is there any impact on site security (fences, perimeter, new site entrances / exits, etc.)
14 | Structural Issues - Will the Project involve one or more of the following
| 14.01 | Permanently or temporarily remove any structural column or post, beam or joist, bearing wall (whether brick, block, concrete, wood or metal stud walls system), floor, wall, or roof sheathing, or bracing member? | [9 empty] | x
| 14.02 | Cutting or drilling through the top one third of the depth of a wood, steel, or concrete beam? | [9 empty] | x
| 14.03 | Cutting or drilling an opening (greater than 3/4" diameter) in any column, post, beam, joist, or brace? | [9 empty] | x
| 14.04 | Adding new equipment (and / or attached supports, piping, conduit, ductwork, etc.) that weighs more than 100 pounds per square foot? | [9 empty] | x
| 14.05 | Adding new equipment (and / or attached supports, piping, conduit, ductwork, etc.) that applies a vertical point load (a load over an area less than two square feet) of more than 2000 pounds? | [9 empty] | x
| 14.06 | Adding new equipment, ductwork, piping, conduit, etc., that applies a horizontal load to the roof, wall, or floor structures (either a thrust, rotational, or vibrating load)? | [9 empty] | x
| 14.07 | Adding additional framing and piping to an existing pipe rack which will increase the height of the pipe support structure? | [9 empty] | x
| 14.08 | Replacement equipment (and / or any attached supports, piping, conduit, and ductwork) that weights 5% more then the previously installed equipment? | [9 empty] | x
| 14.09 | Replacement equipment that provides significantly greater rotational or vibrating loads than the previously installed equipment? | [9 empty] | x
| 14.1 | Cutting holes or openings in an elevated floor system? | [9 empty] | x
| 14.11 | Cutting holes or openings in foundation walls? | [9 empty] | x
| 14.12 | Digging near an interior or exterior column or wall? | [9 empty] | x
| 14.13 | Adding or moving equipment, piping, or other loads, and supporting them from areas of framing or structural members, which have been designated as "near maximum stress" or "over maximum stress"? | [9 empty] | x
| Note: | If the answer to any of the above is "yes", structural requirements will impact your project, and may cause a change in scope. A Structural Risk Assessment must be completed as part of the ORA.
15 | Building Code Compliance - 1st Round (Does the project involve one or more of the following?)
| 15.01 | A change of use or occupancy of the building? (Typically, building codes list uses in groups-businesses, assemble educational, mercantile, storage, factory, utility, etc.; a building is considered a MIXED USE where two or more different uses are co-located.) | [9 empty] | x |  | x
| 15.02 | Introduce a new use (operation different from existing) | [9 empty] | x
| 15.03 | Bringing new / additional hazardous materials into a building? | [9 empty] | x |  | x
| 15.04 | New areas for groups of people (office areas, meeting / team rooms, plant wide meeting locations, etc.); over 45 persons at one time is critical. | [9 empty] | x |  | x
| 15.05 | Additional area (square footage, "footprint") and therefore longer exit travel distances? | [9 empty] | x |  | x
| 15.06 | Changes in equipment, or storage layouts (aisles changed)? | [9 empty] | x |  | x
| 15.07 | Changes that obstruct or change exit location or exit routes / paths? | [9 empty] | x |  | x
| 15.08 | Operations or equipment that produce high heat or open flame? | [9 empty] | x |  | x
| 15.09 | Structural changes (cutting openings, hanging equipment from existing structural work, adding loads, etc.)? | [9 empty] | x
| 15.1 | Cutting / drilling non-structural openings in walls, floors, etc., for piping, conduit, cable trays, etc.? | [9 empty] | x
| 15.11 | Removals / demolition that disrupt protection systems, such as sprinkler systems, fire rated walls / floors, rated doors, etc.? Modification or addition of fire protection (sprinklers), and / or alarm systems? | [9 empty] | x |  | x
| 15.12 | Modification of new electrical, plumbing, HVAC components, sub-systems, branches, equipment? HVAC and room air flow planning complete pre and post project work | [9 empty] | x |  | x | x
| Note: | If the answer to any of the above is "yes", building code requirements will impact your project, and may cause a change in scope. A Building Code Assessment must be completed as part of the ORA.
16 | Building Code Compliance - 2nd Round (Fill out if any Questions were answered with a Yes in Round 1)
| 16.01 | Has a code compliance feasibility assessment (any available preliminary concepts, sketches or designs been checked for compliance with building code Provisions; review local or state building code, or facility records for details), been done for the project?
| 16.02 | For new building construction, or modification of existing facilities, etc., has a design professional been placed under contract to assist in the design change, in compliance with the appropriate codes?
| 16.03 | Has a plant or project person been assigned to act as contact and liaison to the code resource?
| 16.04 | Has it been established that the project is "repair" of the building (not new or modification work)? If the answer is yes, does the anticipated cost exceed the dollar amount stated in the code, which triggers the need for a permit?
| 16.05 | Has a Regulatory Permit Plan been written to develop / establish the need for, and the activity for acquiring a building permit?
| 16.06 | Has a comparison and evaluation been done to identify conflicts between the code(s) and other applicable regulations, such as Process Safety Procedures, OSHA, EPA, etc.?
| 16.07 | Does the project involve locating flammable, combustible, or other hazardous materials in close proximity to existing buildings?
| 16.08 | Have alternate, "equivalent", cost effective strategies been discussed, as a way to achieve compliance and safety and noted for use in the project plan?
| 16.09 | Has a person been identified who is accountable for recording and tracking the code compliance of the project under discussion, and for maintaining compliance after work is completed?
17 | Food Safety & HACCP
| 17.01 | Could this create a potential for product physical hazards? | [12 empty] | x
| 17.02 | Could this create a potential for product micro growth? | [12 empty] | x
| 17.03 | Could this create a potential for product chemical contamination? | [8 empty] | x |  |  |  | x
| 17.04 | Will the demolition, construction or installation work present potential product or sanitation/environmental hazards? Develop a cleaning, housekeeping, and auditing schedule for construction areas. Develop a transition plan from construction zone to a GMP zone. (See Construction Activities Policy listed under Company Regulatory Compliance Policy Statements Webpage.) | [8 empty] | x | x |  |  | x | x
| 17.05 | Food safety is included in project budgeting (e.g. increased swabbing, increased cleaning, increased supplies) Temporary update of EMP (environmental monitoring program) to an elevated state before/during/after project work | [9 empty] | x |  |  | x
| 17.06 | Will this project introduce brittle plastic or plastic in the production or food storage area? If so, update glass, brittle plastic, and ceramic program to address any new hazards to the system | [7 empty] | x |  |  |  |  | x
| 17.07 | Is an X-Ray or Metal Detector needed? Identify and approve all CCPs and CPs. | [7 empty] | x |  |  |  |  | x
| 17.08 | Are handwash stations readily accessible to production employees? | [9 empty] | x | x |  | x
| 17.09 | Has employee traffic patterns been evaluated, especially for micro-sensitive plants? | [9 empty] | x | x |  | x
| 17.1 | Has forklift and pallet jack traffic been evaluated, especially for microsensitive plants/ | [9 empty] | x | x | x | x
| 17.11 | Will product flow from raw to clean? Have flow patterns and potential for cross contamination been evaluated? | [9 empty] | x | x |  | x
| 17.12 | Will this project compromise the separation of raw to finished or ready to eat product? | [9 empty] | x |  |  | x
| 17.13 | Has a person been assigned to train Contractors and Hired Services on plant GMP practices and requirements? Deliver GMP, food safety, and Sanitary Design Principles training for contractors | [7 empty] | x |  |  |  | x | x
| 17.14 | Develop/update water control program to address moisture sources in the new system | [8 empty] | x | x |  |  | x
| 17.15 | Temporarily update water control program to address water/moisture during project (condensation, leaks, cleaning) | [8 empty] | x | x |  |  | x
| 17.16 | Update Allergen Control Program to address any changes (cleaning, color coding, storage, drawings) | [8 empty] | x |  |  |  | x
| 17.17 | Agree on time and resource (including inspectors, maintenance, etc.) needs for changeovers to meet Food Safety success criteria | [8 empty] | x |  |  |  | x
| 17.18 | update Sanitation and inspection training | [8 empty] | x
| 17.19 | Debrief and communicate learnings to broader QE and Sanitation communities | [7 empty] | x | x |  |  |  | x
| 17.2 | Controlled entry and exit planning during construction activities | [9 empty] | x |  |  | x
18 | Sanitation and Equipment Design- review pre, post install including FAT.
| 18.01 | New or used: Is equipment easy to disassemble and clean? Can the equipment be disassembled sufficiently to clean all interior parts and sections? Do you have necessary sanitation related equipment, new foamers, hoses, air drops, hand sinks, etc. | [8 empty] | x
| 18.02 | Are there hidden areas? Is equipment free of niches and hard to clean areas? | [8 empty] | x
| 18.03 | Is equipment accessible for cleaning (all the way around) and inspection? Highlight equipment key access points for routine sanitation and maintenance on project engineering installation drawings. | [6 empty] | x |  | x | x |  | x
| 18.04 | Are special tools required for cleaning or to gain access to equipment parts for cleaning? Is it difficult to open or remove access ports? Is a table, platform or other off-floor stand needed to avoid placing clean parts on the floor? Are accessories needed to store clean or change parts? | [8 empty] | x
| 18.05 | Are additional sanitation procedures necessary? | [8 empty] | x
| 18.06 | Does equipment require CIP and/or COP? (Clean in Place, Clean out of Place). Work with SCOE to ensure compliance with specific CIP validation criteria | [8 empty] | x
| 18.07 | Is a COP tank needed? | [8 empty] | x
| 18.08 | Does equipment require sanitizing in place? | [8 empty] | x
| 18.09 | Is there adequate space under the equipment for cleaning? | [8 empty] | x
| 18.1 | Will equipment not be located over a drain grate? Is the plant drain accessible for cleaning and sanitizing? | [8 empty] | x
| 18.11 | What is the equipment constructed from? Is it suitable for the environmental conditions? | [8 empty] | x | x
| 18.12 | Are interactive metals used? Could these present an undesirable outcome later? | [8 empty] | x | x
| 18.13 | Are catch pans needed? Are drains required in catch pans to avoid standing liquids? | [9 empty] | x |  |  | x
| 18.14 | Are exhaust ducts self-draining? | [9 empty] | x |  |  | x
| 18.15 | Could condensation develop on or above equipment? | [9 empty] | x |  |  | x
| 18.16 | Are bulk ingredient supply lines self draining from shut off valve to the mixing vessel? (i.e. included processing aids like CO2) | [9 empty] | x |  |  | x
| 18.17 | Determine the appropriate cleaning method (dry, wet, controlled wet) for all equipment | [8 empty] | x
| 18.18 | Create/update sanitation work instructions (i.e. SSOPs, OPLs, CILs, etc.) w/chemicals and parameters. Update plant approved chemical list based on input from vendors/suppliers/contractors | [8 empty] | x |  |  |  |  | x
| 18.19 | Include food safety Success Criteria Form items in Ecolab (or other chemical supplier) annual objectives | [8 empty] | x |  |  |  | x
| 18.2 | All GMI QRO, Engineering and Sanitation leads complete Sanitary Design Principles course | [8 empty] | x | x |  |  | x
| 18.21 | Update sanitation programs to include new areas/equipment (MSS, Validation report, Verification and Monitoring program, and SSOPs), sanitation after maintenance, special event cleaning, operational cleaning, housekeeping, and janitorial | [8 empty] | x
| 18.22 | Update Pest Control Program | [8 empty] | x |  |  |  | x
| 18.23 | update reporting tools, tracking/trending of completion rates, etc. | [8 empty] | x
| 18.24 | pre op checklist creation/updates | [8 empty] | x
| 18.25 | Develop a Changeover Matrix to address all changeover types (including, but not limited to allergens) | [8 empty] | x
| 18.26 | Temporarily update MSS (master sanitation schedule) and PMs (preventative maintenance) to address environmental changes (e.g. increased frequency of inspection/cleaning, filter changes, metal detectors, CIP, foamers) | [8 empty] | x
| 18.27 | complete an initial clean of incoming equipment (see CQV tab on Success Criteria Form) | [8 empty] | x
| 18.28 | plan for passivation of new stainless steel equipment | [8 empty] | x
| 18.29 | Highlight RTE (ready to eat) vs non-RTE zones and inputs on project engineering drawings. Identify and approve all control points (CCPs & CPs) on the engineering drawings. | [9 empty] | x |  |  | x
| 18.3 | Design for water removal (drains, slopped floors, drip pans, etc.) | [9 empty] | x
| 18.31 | Design for food safety and sanitation utilities needs (hot water, steam, high pressure water, vacuum system, etc.) | [8 empty] | x | x |  |  | x
| 18.32 | Determine open product zone protection plan (e.g. cleanable overheads or shielding) | [9 empty] | x |  |  | x
| 18.33 | Request manuals for all new & used equipment to include cleaning procedures. | [8 empty] | x |  |  |  |  | x
19 | Quality Management
| 19.01 | Has CFT technical resources been briefed on this project?
| 19.02 | Will the change affect how product is handled that could result in product degradation?
| 19.03 | Is an access point needed to sample product?
| 19.04 | Is there an additional controlled atmosphere area? Does it need monitored for temperature or humidity?
| 19.05 | Will new QA checks be needed?
| 19.06 | Has a checkweigher been considered?
| 19.07 | Will there be controls logic to assure the correct product is sent to the packaging line?
| 19.08 | Has auto generating the code date been considered?
| 19.09 | Has a vision system or UPC scanner been considered?
| 19.1 | Will equipment require calibration? If yes, how will this be accomplished?
| 19.11 | Will new packaging be required? If it is new technology, has shelf life and functionality testing been performed?
| 19.12 | Has a person been assigned to train Contractors and Hired Services on plant GMP practices and requirements?
20 | Product Development Functionality
| 20.01 | Will a formula change be required or a new formula developed?
| 20.02 | Is this a new manufacturing process?
| 20.03 | Is product needed for a trial run?
| 20.04 | Is packaging needed for a trial run?
| 20.05 | Are there time or temperature requirements?
| 20.06 | Will rework be generated and how will it be handled?
| 20.07 | Are special requirements needed for Kosher or Organic certification?
| 20.08 | What on-line food safety/quality monitoring type equipment can be included? (i.e. moisture analyzer, color analyzer)
| 20.09 | What level of accuracy is needed for tank level indicators?
| 20.1 | What degree of accuracy is needed for flowmeters?
21 | Regulatory
| 21.01 | Do on-line computerized recording devices for regulated records such as a pasteurizer temperature recorder meet FDA Recordkeeping requirements? Is the system secure, is there an audit trail, is collected data time stamped, are revisions and changes controlled? Include key food safety events to project timeline (e.g. validation, passivation, regulatory inspection) | [12 empty] | x